## Sheet1
Week | Date | Task | Assigned To | Status
Week 1 | 2002-06-01 | Collect phone data from online sources | Joel | Done
Week 1 | 2002-06-01 | Plan and add new feature | Varma | Done
Week 1 | 2002-06-01 | Clean and format the dataset | Luqmaan | Done
Week 1 | 2006-06-01 | Build final dataset with all added features | Varma | Done
Week 1 | 2006-06-01 | Create system to find best phone | Joel | Done
Week 1 | 2006-06-01 | Prepare data so the RAG model undertands it | Luqmaan | Done
Week 2 | 2009-06-01 | Design a simple chatbot interface | Luqmaan | Done
Week 2 | 2009-06-01 | Add phone comparison feature to UI | Varma | Done
Week 2 | 2009-06-01 | Connect model output to chatbot | Joel | Done
Week 2 | 2013-06-01 | Test the chatbot with real user questions | Luqmaan | Done
Week 2 | 2013-06-01 | Creat Project documentation | Varma | Done
Week 2 | 2013-06-01 | Create final presentation slides | Joel | Done